## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated Retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 2 | 4 | 4 | 4*2*4=32 | team leader and all members | 2025-05-18 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one dropped the class so far | Open
| add new team members | One or more team members added to the team | 2 | 3 | 3 | 4*3*3=36 | team leader and all members | 2025-05-18 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one added the team so far | Open
Requirements | unclear requirements | unclear requirements defined in each feature | 3 | 3 | 3 | 3*3*3=27 | team leader and all members | Ongoing | Work with requirements lead |  | Open
| scope creep | scope expanded in a feature/ticket | 3 | 3 | 3 | 3*3*3=27 | team leader and all members | Ongoing | Work with requirement lead and team lead |  | Open
| constant requirements changes | new feature added | 3 | 3 | 3 | 3*3*3=27 | team leader and all members | Ongoing | Work with requirement lead and team lead |  | Open
Management | improper planning | Estimates in an iteration are too optimistic or pessimtic | 2 | 4 | 4 | 4*2*4=32 | Team leader | Ongoing | Update the Timeline for the next iteration based on the veolicty in the current iteration |  | Open
Technology competence | Not familiar with the Spring Security | Will need to protect our REST APIs so only authenticated and authorized users have access. Spring framework provides Spring Security feature, however Im not familiar with so will need to research this topic. | 5 | 5 | 4 | 1*1*4=4 | Team leaders | 2025-05-12 | Go through the Spring Security guides such as Method Security & Authorize HttpServletRequests. |  | Open
| Not familiar with the programming language used | Not familiar with aspects of React, Java or Spring Boot | 3 | 3 | 3 | 3*3*3=27 | team leader and all members | Ongoing | Ongoing knowledge sharing session during group meetings |  | Open
Design and implementation | Improper design |  | 3 | 3 | 3 | 3*3*3=27 | team leader and all members | Ongoing | design review meetings |  | Open
| Messy code |  | 3 | 3 | 3 | 3*3*3=27 | team leader and all members | Ongoing | Refactor code as we go |  | Open
Testing | Not enough testing | PR is missing unit tests or manual testing is missing crucial test cases | 3 | 3 | 3 | 3*3*3=27 | team leader and all members | Ongoing | Ensure PR has unit tests, CI/CD makes sure test pass. |  | Open
Integration and deployment | Not enough time for integration and deployment | feature is not deployed to production | 4 | 3 | 3 | 2*3*3=18 | team leader and all members | 2025-05-18 | Add Deploy to Production Column in Github Projects |  | Open
The team member who is adding the new feature should be the one who determines what is correct for the new functionality that was added.
Work together as a team to make sure each developer has the same environment. This is useful so that there aren't accidental bugs added due to environment issues.