## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (Individual + Group Meeting) (h) | Total Individual work time (cumulative time spent working on tasks and projects) (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 5/10/25 - 5/14/25 | SPPP | N/A | N/A | N/A | 0 | 0 | 0 | 0 | 0 | 38 | 43.5 | 5 | 16 | 1 | 1.5 | 4 | 1.5 | 4.5 | 1
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Arshdeep Dhillon | Iteration 0 worked on Overview section and expanded others sections | [7 empty] | Lead meetings
Jin Hao Li | Iteration 0 worked on Management Plan | [7 empty] | Meeting Minutes

## studentName
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | Use chatgpt to research Django, and elicitate some high level requirements, which we discussed in the team meeting, Use copilot to generate an initial code sketlon, though it requires some manual modification to get it running | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6

## Jin Hao Li
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/14 | 12 | 7 | 5 | 0 - SPPP document 1 - Meeting Minutes 2 - setup git 3 - presentation | 5 | 1 | 1 | 1 | [5 empty] | 1. Management Plan of SPPP 2. Meeting Minutes for all three meetings 3. Presentation

## Jie Shi
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/13-05/14 | 5 | 4 | 1 | 0 - SPPP document, git, Requirements for a complete software, performance baseline and architectural bottlenecks, apache JMeter 1 - a few requirements features we may develop 2 - setup individual uses github desktop | 3 | 0.5 | 0.5 | [5 empty] | Use Chatgpt to know about requirements for a complete software, performance baseline, performance testing, architectural bottlenecks about a software and apache JMeter. | 1. few requirements features we may develop |  |  | 0 - Continue to learn the tools you may need to complete these requirements 1 - Continue to add any requirements that may be needed 3 - Try to implement some basic features with team | 6

## Arshdeep Dhillon
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security, Project Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | AI tool log(any AI tools used for what tasks, is it helpful? How do you use the results) | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | May 5 - May 14 | 20 | 15.5 | 4.5 | 0 - learn Github and the functionalities it provides such as Github Actions, Github Projects, GitHub Protection Rules for branches. Learned VSCode's Devcontainer feature which will be used as our development environment. 2 - learn features provided by Springboot such as RESTAPI and Spring Security. 3 - Implemented a proof of concept of the backend using Springboot, which contains one service,one model using JPA, one respository, two GET endpoints. 4 - Tested the Springboot server by using JUnit4 for unit tests and PostMan application for testing the two RESTAPIs. 5 - Setup the first team meeting using Discord event. Setup second team meeting using Discord event. Expand and clarify the sections in SPPP documents. | 11 |  | 0.5 | 3 | 1.5 | 4.5 | 1 |  | Used chatgpt to list out features of Github which are most appropriate for a team. | 1. Write up the Overview section of SPP. | 1. Member mentioned about Django for backend, will need to research the framework. 2. Unfamiliarity with Spring Security. 3. The sections of SPPP document need to be expaned and made clear. 4. Took longer than expected setting up VSCode's Devcontainer due to my Virtual Machine crashing and figuring out the appropriate devcontainer setup for the project. | 1. Will use Spring framework for backend because of familiarity 2. Going through Spring guides on setting up Spring security so that only authenticated users can make requests and specific users can access certain endpoints. 3. Updated sections of SPPP document which needed to be expanded for clarity and completeness. |  | 15.5
2 | May 15 - May 21